## SEPT Feature Project - Planning
Title | Assignees | Status | Labels | Iteration | Estimate | Milestone | Repository | URL | Linked pull requests
Price comparison | udit710 | Done | Type: Story | Iteration | 1 | Milestone 1 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/1
Comparison view design/wireframe | udit710 | Done | Area: Frontend, Type: Task | Iteration | 1 | Milestone 1 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/2
Item Checkout | ra5h1k | Done | Type: Story | Iteration | 1 | Milestone 1 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/3
Saved Items List | udit710 | Done | Type: Story | Iteration 2 | 1 | Milestone 1 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/6
Search Items | IbrahimAshhab | Done | Type: Story | Iteration | 1 | Milestone 1 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/13
Product Detail | ra5h1k | Done | Type: Story | Iteration | 1 | Milestone 1 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/7
Saved Items design/wireframe | udit710 | Done | Area: Frontend, Type: Task | Iteration | 1 | Milestone 1 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/8
Item Checkout/wireframe | ra5h1k | Done | Area: Frontend, Type: Task | Iteration | 1 | Milestone 1 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/10
Price Comparison | udit710 | Done | Type: Story | Iteration | 1 | Milestone 1 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/9
Product Detail/wireframe | ra5h1k | Done | Area: Frontend, Type: Task | Iteration | 1 | Milestone 1 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/11
Home page Wireframe | Vidyut03 | Done | Area: Frontend, Type: Task | Iteration 2 | 1 | Milestone 1 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/12
Architecture | AbhijeetK520 | Done | Type: Task | Iteration | 1 | Milestone 1 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/14
Search Items API for search button | IbrahimAshhab | Done | Area: Backend | Iteration | 7 | Milestone 1 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/15
Navigation Bar | IbrahimAshhab | Done | Area: Frontend | Iteration | 1 | Milestone 1 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/16
Category Selection Wireframe | Vidyut03 | Done | Area: Frontend, Type: Task | Iteration 2 | 1 | Milestone 1 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/18
Delivery options | IbrahimAshhab | Done | Type: Story | Iteration | 1 | Milestone 1 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/19
Home Page Story | Vidyut03 | Done | Type: Story | Iteration 2 | 1 | Milestone 1 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/20
Category Selection | Vidyut03 | Done | Type: Story | Iteration 2 | 1 | Milestone 1 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/17
Discount Page | AbhijeetK520 | Done | Type: Story | Iteration | 1 | Milestone 1 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/24
Notifications and Alerts | AbhijeetK520 | Done | Type: Story | Iteration | 1 | Milestone 1 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/21
Notification Tab | AbhijeetK520 | Done | Area: Frontend, Type: Task | Iteration 2 | 1 | Milestone 1 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/22
Saved Items List | udit710 | Done | Type: Story | Iteration 2 | 1 | Milestone 1 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/23
Price Cmparision | udit710 | Done | Type: Story | Iteration | 1 | Milestone 1 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/25
Saved Items | udit710 | Done | Type: Task | Iteration | 1 | Milestone 1 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/26
Design the database schema. | AbhijeetK520 | Done | Area: Backend | Iteration | 1 | Milestone 1 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/37
Home Page | udit710 | Done | Type: Story | Iteration 2 | 1 | Milestone 1 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/29
Category Dropdown | udit710 | Done | Type: Story | Iteration 2 | 1 | Milestone 1 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/30
Category Dropdown | udit710 | Done | Type: Story | Iteration 2 | 1 | Milestone 1 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/31
Product Details Section | udit710 | Done | Type: Story | Iteration 2 | 1 | Milestone 1 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/32
Product Details Section | udit710 | Done | Type: Story | Iteration 2 | 1 | Milestone 1 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/33
Filter Dropdown | udit710 | Done | Type: Story | Iteration 2 | 1 | Milestone 1 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/34
Filter Dropdown | udit710 | Done | Type: Story | Iteration 2 | 1 | Milestone 1 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/35
Item Checkout Page | udit710 | Done | Type: Story | Iteration 2 | 1 | Milestone 1 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/36
Request data from product api in frontend | AbhijeetK520 | Done | Area: Frontend, Type: Task | Iteration 3 | 6 | Milestone 2 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/76 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/108
Use Product API to show product details in product page | AbhijeetK520 | Done | Area: Frontend, Type: Task | Iteration 3 | 10 | Milestone 2 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/60 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/108
API Endpoint to get filtered products | AbhijeetK520 | Done | Area: Backend, Type: Task | Iteration 3 | 7 | Milestone 2 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/57 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/118, https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/119
Request data from review api in frontend | AbhijeetK520 | Done | Area: Frontend, Type: Task | Iteration 3 | 6 | Milestone 2 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/75 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/108
Convert frontend to create-react-app project | Vidyut03 | Done | Area: Frontend, Type: Task | Iteration 3 | 6 | Milestone 2 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/38 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/39
Navbar | Vidyut03 | Done | Area: Frontend, Type: Task | Iteration 3 | 6 | Milestone 2 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/5 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/40
Search Results page implementation | Vidyut03 | Done | Area: Frontend, Type: Task | Iteration 3 | 6 | Milestone 2 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/42 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/129
Product Detail Page | udit710 | Done | Area: Frontend, Type: Task | Iteration 3 | 6 | Milestone 2 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/41 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/97, https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/108
Set up the development environment. | AbhijeetK520 | Done | Area: Backend, Type: Task | Iteration 3 | 3 | Milestone 2 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/27
Setup API Endpoints to get list of all products | AbhijeetK520 | Done | Area: Backend, Type: Task | Iteration 3 | 7 | Milestone 2 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/56 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/48
Setup github workflow | AbhijeetK520 | Done | Type: Task | Iteration 3 | 2 | Milestone 2 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/55 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/49, https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/53
API Endpoint to update products | AbhijeetK520 | Done | Area: Backend, Type: Task | Iteration 3 | 8 | Milestone 2 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/58 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/48
API Endpoint to insert products | AbhijeetK520 | Done | Area: Backend, Type: Task | Iteration 3 | 8 | Milestone 2 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/59 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/48
Add Routing for Search Page | Vidyut03 | Done | Area: Frontend, Type: Task | Iteration 3 | 6 | Milestone 2 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/62 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/47, https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/118, https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/129
Add Routing for Home Page | Vidyut03 | Done | Area: Frontend, Type: Task | Iteration 3 | 6 | Milestone 2 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/64 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/51, https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/54
Write tests for Review API | Vidyut03 | Done | Area: Backend, Testing | Iteration 3 | 4 | Milestone 2 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/72 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/73, https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/86
API Endpoints to get user's orders | udit710 | Done | Area: Backend, Type: Task | Iteration 3 | 7 | Milestone 2 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/68 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/91
API Endpoints to get product reviews | Vidyut03 | Done | Area: Backend, Type: Task | Iteration 3 | 7 | Milestone 2 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/69 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/73, https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/86
API Endpoint to get user details | udit710 | Done | Area: Backend, Type: Task | Iteration 3 | 3 | Milestone 2 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/70 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/111
use docker-compose in AWS Beanstalk | AbhijeetK520 | Done | Area: Architecture, Type: Task | Iteration 4 | 8 | Milestone 3 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/229
Host Docker Images to AWS ECR | AbhijeetK520 | Done | Area: Architecture, Type: Task | Iteration 4 | 8 | Milestone 3 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/228
Test cart items api | udit710, Vidyut03 | Done | Area: Backend, Testing, Type: Task | Iteration 4 | 4 | Milestone 3 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/84 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/242
Login should redirect to previous page | Vidyut03 | Done | Area: Frontend, Type: Task | Iteration 4 | 3 | Milestone 3 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/235 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/236
Show offers based on discounts and categories in homepage | ra5h1k | Done | Area: Frontend, Type: Task | Iteration 3 | 6 | Milestone 2 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/116 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/138
Request data from backend api for cart | udit710 | Done | Area: Frontend, Type: Task | Iteration 4 | 5 | Milestone 3 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/82 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/221
Login Page Frontend | AbhijeetK520, udit710 | Done | Area: Frontend, Type: Task | Iteration 4 | 5 | Milestone 3 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/103 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/190
Signup page frontend | IbrahimAshhab | Done | Area: Frontend, Type: Task | Iteration 4 | 5 | Milestone 3 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/105 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/190
Fix frontend docker application | AbhijeetK520 | Done | Area: Frontend, Type: Task | Iteration 4 | 7 | Milestone 3 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/160 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/168
Migrate from flyway to mysql | AbhijeetK520 | Done | Area: Architecture, Type: Task | Iteration 4 | 6 | Milestone 3 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/169 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/168
Setup docker-compose with mysql | AbhijeetK520 | Done | Area: Architecture, Type: Task | Iteration 4 | 8 | Milestone 3 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/170 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/168
Frontend testing for search results page | Vidyut03 | Done | Area: Frontend, Testing | Iteration 3 | 3 | Milestone 2 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/87 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/95
Test Cases for Orders API | udit710 | Done | Area: Backend, Testing | Iteration 3 | 4 | Milestone 2 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/90
Frontend tests for product detail page | Vidyut03 | Done | Area: Frontend, Testing | Iteration 3 | 3 | Milestone 2 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/96 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/97
User login page wireframe | Vidyut03 | Done | Area: Frontend, Type: Task | Iteration 3 | 1 | Milestone 2 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/79
User sign up page wireframe | Vidyut03 | Done | Area: Frontend, Type: Task | Iteration 3 | 1 | Milestone 2 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/80
User login page story | Vidyut03 | Done | Area: Frontend, Type: Story | Iteration 3 | 1 | Milestone 2 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/77
User sign up page story | Vidyut03 | Done | Area: Frontend, Type: Story | Iteration 3 | 1 | Milestone 2 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/78
Fix footer placement frontend | IbrahimAshhab | Done | Area: Frontend, Type: Bug | Iteration 3 | 6 | Milestone 2 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/85 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/50, https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/74, https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/107
Update Product Details in Database to store discounts %, total price and discounted price | IbrahimAshhab | Done | Area: Backend, Type: Task | Iteration 3 | 9 | Milestone 2 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/66 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/112
Test Cases for User API | udit710 | Done | Area: Backend, Type: Task | Iteration 3 | 3 | Milestone 2 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/113 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/115
Use Search API to show filtered product in search page | Vidyut03 | Done | Area: Frontend, Type: Task | Iteration 3 | 6 | Milestone 2 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/61 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/129
Add Category field to data model | ra5h1k | Done | Area: Backend, Type: Task | Iteration 3 | 6 | Milestone 2 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/117 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/122, https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/123
Add Routing for Product Details Page | ra5h1k | Done | Area: Frontend, Type: Task | Iteration 3 | 6 | Milestone 2 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/63 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/137
Add Product Review component to Product Details page | ra5h1k | Done | Area: Frontend, Type: Task | Iteration 3 | 6 | Milestone 2 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/120 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/124
Implement Search results data in frontend | Vidyut03 | Done | Area: Frontend, Type: Task | Iteration 3 | 6 | Milestone 2 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/128 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/129
Fix productDeatils test frontend | Vidyut03 | Done | Area: Frontend, Testing, Type: Bug | Iteration 3 | 3 | Milestone 2 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/130 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/134
Pending Meeting minutes for August | udit710 | Done | Type: Task | Iteration 3 | 2 | Milestone 2 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/131 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/133
Meeting minutes for September | IbrahimAshhab | Done | Type: Task | Iteration 3 | 2 | Milestone 2 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/132
Meeting minutes for September week 2 | IbrahimAshhab | Done | Type: Task | Iteration 3 | 2 | Milestone 2 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/143
Update Transaction_Item table to contain product details id | ra5h1k | Done | Area: Backend, Type: Task | Iteration 3 | 2 | Milestone 2 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/67
Finish backend tests | Vidyut03 | Done | Area: Backend, Testing, Type: Task | Iteration 3 | 5 | Milestone 2 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/141 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/142
Fix Offers | Vidyut03 | Done | Area: Frontend, Type: Bug, Type: Task | Iteration 3 | 2 | Milestone 2 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/144 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/149, https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/151
Meeting Minutes Week 1 | ra5h1k | Done | Type: Task | Iteration 3 | 2 | Milestone 2 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/146 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/153
Add Queries in schema | udit710 | Done | Area: Backend, Type: Task | Iteration 3 | 3 | Milestone 2 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/165
Use subcategory api in frontend | Vidyut03 | Done | Area: Frontend, Type: Task | Iteration 4 | 5 | Milestone 3 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/171 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/173
Fix subcategory apis | Vidyut03 | Done | Area: Backend, Type: Bug | Iteration 4 | 5 | Milestone 3 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/172 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/173
Implement saved_item/cart page | udit710 | Done | Area: Frontend, Type: Task | Iteration 4 | 5 | Milestone 3 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/81 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/221
Implement cart items api | udit710 | Done | Area: Backend, Type: Task | Iteration 4 | 8 | Milestone 3 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/83 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/183
Update notification frontend | AbhijeetK520, IbrahimAshhab | Done | Area: Frontend, Type: Task | Iteration 4 | 5 | Milestone 3 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/99 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/214
Further backend testing | Vidyut03 | Done | Area: Backend, Testing | Iteration 4 | 7 | Milestone 3 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/220 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/230
Frontend general testing | Vidyut03 | Done | Area: Frontend, Testing | Iteration 4 | 6 | Milestone 3 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/218 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/219
Fix Product Discount % | AbhijeetK520 | Done | Area: Frontend, Type: Task | Iteration 4 |  | Milestone 3 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/216 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/215
Implement add review feature | Vidyut03 | Done | Area: Frontend, Type: Task | Iteration 4 | 5 | Milestone 3 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/175 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/176
Test navbar frontend | Vidyut03 | Done | Area: Frontend, Testing | Iteration 4 | 3 | Milestone 3 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/101 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/217
Make Notification API | AbhijeetK520, IbrahimAshhab | Done | Area: Backend, Type: Task | Iteration 4 | 8 | Milestone 3 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/98 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/222
Connect Notification API | AbhijeetK520, IbrahimAshhab | Done | Area: Frontend, Type: Task | Iteration 4 | 6 | Milestone 3 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/28 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/227
Implement login aip in frontend | Vidyut03 | Done | Area: Frontend, Type: Task | Iteration 4 | 5 | Milestone 3 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/200 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/202
Implement sign-up api in frontend | Vidyut03 | Done | Area: Frontend, Type: Task | Iteration 4 | 5 | Milestone 3 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/201 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/202
Add frontend user session storage | Vidyut03 | Done | Area: Frontend, Type: Task | Iteration 4 | 5 | Milestone 3 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/199 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/202
Create user authentification in apis | Vidyut03 | Done | Area: Backend, Type: Task | Iteration 4 | 10 | Milestone 3 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/174 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/195
Update feature for review | Vidyut03 | Done | Area: Frontend, Type: Task | Iteration 4 | 3 | Milestone 3 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/178 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/180
Delete feature for review | Vidyut03 | Done | Area: Frontend, Type: Task | Iteration 4 | 3 | Milestone 3 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/179 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/180
Fix cart Items bug | udit710, Vidyut03 | Done | Area: Backend, Type: Bug | Iteration 4 | 5 | Milestone 3 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/184 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/185, https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/186
Fix delete review reload issue | Vidyut03 | Done | Area: Frontend, Type: Bug | Iteration 4 | 1 | Milestone 3 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/196 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/197
Create offers page | Vidyut03 | Done | Area: Frontend, Type: Task | Iteration 4 | 6 | Milestone 3 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/203 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/210
Implement user accouts with reviews | Vidyut03 | Done | Area: Frontend, Type: Task | Iteration 4 | 4 | Milestone 3 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/204 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/207
Fix issue subcategories not working when logged in | Vidyut03 | Done | Area: Frontend, Type: Bug | Iteration 4 | 4 | Milestone 3 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/208 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/209
Signup page frontend tests | Vidyut03 | Done | Area: Frontend, Testing | Iteration 4 | 3 | Milestone 3 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/106 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/219
Orders Page Frontend | ra5h1k, udit710 | Done | Area: Frontend, Type: Task | Iteration 4 | 5 | Milestone 3 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/177 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/256
Implement add to cart in frontend | udit710, Vidyut03 | Done | Area: Frontend, Type: Task | Iteration 4 | 3 | Milestone 3 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/224 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/233
fix header for superprice | udit710 | Done | Area: Frontend, Type: Bug | Iteration 4 | 1 | Milestone 3 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/225 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/226
Store user address | Vidyut03 | Done | Area: Backend, Type: Task | Iteration 4 | 5 | Milestone 3 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/248 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/247
Test frontend cart page | Vidyut03 | Done | Area: Frontend, Testing | Iteration 4 | 3 | Milestone 3 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/102 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/246
Test notification frontend | Vidyut03 | Done | Area: Frontend, Testing | Iteration 4 | 3 | Milestone 3 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/100 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/245
Backend integration tests | Vidyut03 | Done | Area: Backend, Testing | Iteration 4 | 7 | Milestone 3 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/232 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/244
Search page price fix | Vidyut03 | Done | Area: Frontend, Type: Bug | Iteration 4 | 2 | Milestone 3 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/237 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/238
Test Cases for Notification API | IbrahimAshhab, Vidyut03 | Done | Area: Backend, Testing | Iteration 4 | 4 | Milestone 3 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/114 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/231
Login page frontend tests | Vidyut03 | Done | Area: Frontend, Testing | Iteration 4 | 3 | Milestone 3 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/104 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/219
Fix quantity error in add to cart | udit710 | Done | Area: Frontend, Type: Bug | Iteration 4 | 1 | Milestone 3 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/240 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/241
Create Minutes For Meetings | udit710 | Done | Type: Story, Type: Task | Iteration 4 | 2 | Milestone 3 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/243
Fix meeting minutes pdfs | udit710 | Done | Type: Task | Iteration 4 | 1 | Milestone 3 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/261 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/260
Fix add to cart | udit710 | Done | Area: Frontend, Type: Bug | Iteration 4 | 1 | Milestone 3 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/263 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/264
Update product images | udit710 | Done | Area: Backend, Type: Task | Iteration 4 | 1 | Milestone 3 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/265 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/267
clean files | udit710 | Done | Area: Frontend, Type: Task | Iteration 4 | 2 | Milestone 3 | cosc2299-sept-2023/team-project-group-p02-07 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/266 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/268

## Task Per Iteration Per Mileston
Count of Milestone | Iteration
Milestone | Iteration | Iteration 2 | Iteration 3 | Iteration 4 | Grand Total
Milestone 1 | 18 | 15 |  |  | 33
Milestone 2 |  |  | 44 |  | 44
Milestone 3 |  |  |  | 50 | 50
Grand Total | 18 | 15 | 44 | 50 | 127

## Task per Label
Labels | Count of Title
Area: Frontend, Type: Task | 44
Type: Story | 21
Area: Backend, Type: Task | 18
Type: Task | 8
Area: Frontend, Testing | 8
Area: Frontend, Type: Bug | 7
Area: Backend, Testing | 5
Area: Architecture, Type: Task | 4
Area: Frontend, Type: Story | 2
Area: Backend, Testing, Type: Task | 2
Area: Backend, Type: Bug | 2
Area: Backend | 2
Area: Frontend | 1
Type: Story, Type: Task | 1
Area: Frontend, Testing, Type: Bug | 1
Area: Frontend, Type: Bug, Type: Task | 1
Grand Total | 127